## Slide 1: General Education Implementation Faculty Senate – May 11, 2023

## Slide 2: General Education Implementation
Provost
Steering Committee
Core Team
Organizational Change Management
Pedagogical Support and Development
Operations
Policy and Process (Baccalaureate Core Committee)
Faculty Senate Processes
Administrative Processes
Core Team Committees
% Decisions
70%
20%
8%
2%
Retired: Learning Outcomes, Criteria, and Rationale (LOCR) ​
Notes: McKenzie
Implementation Components
Development of Learning Outcomes, Criteria and Rationale (LOCR) for each category of the new general education curriculum
Course development/revisions to meet the new LOCRs and faculty support/resources
Establish policy and process standards for the governance of the new general education curriculum
Operational implementation in university systems
Development of a phased training, communication and marketing roll out of the new general education curriculum to relevant stakeholders
Transition plan from old curriculum to new curriculum - work with students to ensure minimal impact for those completing old curriculum and those completing the new curriculum
LOCR workgroups were not responsible for budget considerations and larger picture implementation issues

## Slide 3
April 13, 2023
  Faculty Senate Approved Learning Outcomes, Criteria, and Rationale (LOCR)
Summer 2023 – January 31, 2025
Course development and redesign institutes
Fall 2023 – January 31, 2025
Bacc Core Committee – review and approval of courses
Summer 2025
General Education goes live!
Implementation Project Timeline
January 31, 2025
Initial set of courses approved through curriculum process (CIM)
July 2023 – June 2024
Phase I Installation
July 2024 – January 31, 2025
Phase II Installation
Notes: McKenzie -
Long timeline – low intensity
Short timeline – high intensity work
Long processes does not mean more engagement, short processes are better for a heavy lift like this, there was substantial engagement. No matter if we took longer or had this short process, people would have felt rushed - don't mistake exhaustion for rigor

## Slide 4: BCC – Gen Ed Policies & Ops
Current status: Published on GenEd website:
  Double counting: Allow students to count program-embedded Gen Ed courses
  Dual listing​: Courses must register in a single Gen Ed category
  Course levels​: LOCR-defined links between categories, courses and course levels
  Accessible language​: Use of commonly understandable language for students
  De minimis criterion​: Criteria for minimal content to be eligible for a Gen Ed category
  Intra-category diversification​: Taking different subjects within a single category
  Use of OSU learning platform​: For syllabus, grades, class communication
  Course materials (OER): Stresses the need for OER Gen Ed course materials
  New/Change course proposal review process
  Class sizes: LOCR-defined maximum class sizes, university minimum class policy
  Faculty development: Prof. dev. for faculty to develop and teach Gen Ed courses
  Course credit transfer: Transfer of course credit from other schools and institutions

## Slide 5: BCC – Gen Ed Policies & Ops (Cont'd)
Remaining:
Learning Outcome Assessment: In progress...
Variances & exceptions
No policies (after discussion):
Grade minima
Expertise
Syllabus visibility
Non-GenEd units

## Slide 6: Course (re)design
Corvallis and Cascades*:
Course Adaptation and Design Institute (CADI):
  Mandatory for everyone adapting or designing a GenEd course.
  Product: Complete CIM proposal, Course map, Course design.
    One day, synchronous.
    DPO, WIC, SeSo, and Transitions will have additional specialty professional development (PD) required.
Ecampus*:
Developing Online Course (DOC)
Redeveloping Online Course (ROC)
*Funding is available for (re)design

## Slide 7: Teaching in GenEd
All who teach in GenEd will be required to participate in a Professional Development Module:
  CTL developed, Asynchronous, Canvas, ~1-3 hours
  Objective: Provide evidence-informed practices to aid course design and development of course map, syllabus, assignments, and assessments.
  On-demand
  Recertification required every 3 years

## Slide 8: FAQs
I am (re)designing on-campus & on-line courses, do I need both CADI & DOC/ROC?
  Answer: Yes.
Are CADIs going to be accessible remotely?
  Answer: Yes.
I am developing different courses, do I go through different CADIs?
  Answer: No
Are CADIs Gen Ed course category specific?
  Answer: No, the CADI covers all Gen Ed categories. However, some Gen Ed categories; e.g., WIC, DPO, SeSO, etc. may have additional professional development requirements.
If I am teaching but not developing a course, do I have to attend CADI?
  No (on-campus class): Enroll in a self-guided Canvas Guide for key material.
  Yes (on-line class): Teaching Online Course or New Instructor Training.

## Slide 9: Phase I Installation (July 2023-June 2024)
Faculty to Faculty: BCC solicits – process of sharing data with colleges/faculty to inform decisions (May/June ‘23)
Colleges complete a "statement of intent” of the courses they plan to (re-)design and submit (in CIM
Faculty re(design) courses through CADI
Course review process
BCC will review the following in AY 23-24 - Designator limits (+2 per designator/category); Z courses (CCN), Series courses (BIO 10X)
Course approvals are added to list for Summer 2025 launch
DPO and WIC have specific additional trainings
Transitions and SeSo will be folded into CADI
Faculty submits proposal in CIM
College leadership teams are prepared for install plan and encouraged to work with faculty
(rolling due dates per quarter for following quarter Course Adaptation and Design Institute – CADI)
Notes: Colleges need to communicate their intentions for development, this needs to be provided by the designee on an on-going basis, with a first-check-in of October 1 at the latest:
Schedule of quarterly due dates
Intentions by July 1, 2023 (for Sept. CADI)
October 1, 2023 (for Winter CADI)
Jan 1, 2024 (for Spring CADI)
April 1, 2024 (for Summer CADI)
+ deadlines and when things open
+ CIM course proposal form won't open until September
+ CADI deadlines
(CADI – Course Design and Adaptation Institute) - 1-2 days (general to specific)
Add to Statement form –
current course number and intended course designator and number for level change
1st, 2nd, 3rd choice for CADI
Course proposal form adds -
OER info
Signature Assignment

## Slide 10: Phase II Installation (June 2024 – January 2025)
College data-driven decisions encouraged:
Colleges complete a "statement of intent” of the courses they plan to (re)design and submit in CIM
(rolling due dates per quarter for following quarter Course Adaptation and Design Institute – CADI)
Faculty re(design) courses through CADI
Course review process
Course approvals are added to list for Summer 2025 launch
DPO and WIC have specific additional trainings
Transitions and SeSo will be folded into CADI
Faculty submits proposal in CIM
BCC will review the following in AY 24-25 - Designator limits (+3 per designator/category); Z courses (CCN), Series courses (BIO 10X)
Notes: Colleges need to communicate their intentions for development, this needs to be provided by the designee on an on-going basis, with a first-checkin of October 1 at the latest:
Schedule of quarterly due dates
Intentions by July 1 (for Sept. CADI)
October 1 (for Winter CADI)
Jan 1 (for Spring CADI)
April 1 (for Summer CADI) (for future catalog year add)

## Slide 11: Statement of Intent Deadlines
Phase I Statement of Intent (CIM) Submission Dates and Deadlines:
  July 1, 2023 (for September 2023 CADIs)
  October 1, 2023 (for Winter 2024 CADIs)
  January 1, 2024 (for Spring 2024 CADIs)
  April 1, 2024 (for Summer 2024 CADIs)
Phase II Statement of Intent (CIM) Submission Dates and Deadlines:
  July 1, 2024 (for September 2024 CADIs)
  October 1, 2024 (for Winter 2025 CADI for future catalog year additions to the curriculum)
  January 1, 2025 (for Spring 2025 CADI for future catalog year additions to the curriculum)
  April 1, 2025 (for Summer 2025 CADI for future catalog year additions to the curriculum)

## Slide 12: Bacc Core Tableau Dashboard in CORE